## Slide 1: CA from 1000’
Construction administration basics & principles

## Slide 2: Agenda
Communication & Relationships
Timeline & Definitions
Site Visits & Field Reports

## Slide 3: Communication & Relationships
1

## Slide 4: Roles
On site, Phone, Email; use each of these at appropriate times to your advantage.
On site meetings are required, especially when tensions are high.
Phone calls are your best and most readily available form of communication for quick, informal, responses.
Use your email lightly but especially for documentation and formal decisions.
Owner + Architect + Contractor
The greatest breakdown in construction projects stems from a lack of communication between these 3 primary roles. As Architect, we are to nurture these relationships and keep the lines of communication open to the best of our abilities and with the tools readily available to us.

## Slide 5: Architect’s In House
Project Manager & Administrative Assistant
As PM over any project, you are responsible for all aspects of that project.
Delegate tasks, but keep track and double back to make sure tasks are being performed.
Administrative Assistants are there to do just that, assist.
Redundancy is work can be a good thing. Not everyone gets it right the first time, so check.
Dale Specifics as of Summer 2022:
  AIA Docs by Administrative Assistants
  Field Reports & Site Visits by In House CA
  Log Tacking by Administrative Assistants & PMs

## Slide 6: Timeline & Definitions
2

## Slide 7: Definitions
RFI – Request for Information
Submittal – product information
WCPR – Work Change Proposal Request
CCD – Construction Change Directive
CO – Change Order
ASI – Architect’s Supplemental Instruction
Pay App – Application for Payment
SOV – Schedule of Values
Punch List – developed task list
Formal AIA Document
Formal AIA Document
Formal AIA Document
Formal AIA Document
Formal AIA Document
Formal AIA Document

## Slide 8: Bid Day to Warranty
Responsibilities
As PM, there are many small tasks that must be handled during the CA phase of construction. Some tasks are responsive (ie replying to contractor initiated RFI’s, submittals, pay applications, & change order requests OR owner initiated scope changes). Other tasks, we must take a proactive role (ie letter of recommendation, contract, field reports, certificate of substantial completion, & punch lists).
Negotiations
Initial Submittals
Field Reports & Pay Apps
Substantial & Closeouts
Warranty
Key your logs updated!

## Slide 9: Site Visits & Field Reports
3

## Slide 10: Site Visits
Representation
When you are on the site, you represent Dale Partners to the world. Your presence is just another key in developing good relationships.
With the contractor, we should be helpful but discerning.
With the owner, we should be helpful and encouraging.
Walk the Site (all of it)
Meet with the Super
Review work Performed
Discuss Future Work
Bring up Issues
Not Slothful in bringing up issues Able to see discrepancies
Able to translate their concerns Not bemoaning the contractor’s work

## Slide 11: Field Reports
Content
  Be to the point; descriptive words can help or hurt, so be careful what you write
  Give information about progress
  Give information about contractor effort
  Reserve judgements concerning quality for very specific usages
Pictures (a picture is worth a thousand words)
  Takes lots
  Include regular photo positions for help is seeing progress and orientation; Not all photos have to be major issues; if new construction, get regular photos of all exterior elevations
  Use words with photos to help in understanding
  Choose the best vantage to photo issues so that they can be readily seen
Regularity
  Every time you make a site visit, someone should know you were there, in writing
  Field Reports give our clients some pace knowing that we are on the site

## Slide 12
New Ceilings (what’s wrong?)

## Slide 13
New Doors (what’s wrong?)

## Slide 14
New Floors (what’s wrong?)

## Slide 15: Purpose, Strategy, & Tools
To continue our relationship with clients & serve them
Purpose
Formal & Informal Documents and correspondence
Tools
Use documentation to communicate and protect
Strategy
Our presence and communication
Tools